Changing this number will scroll the Gantt Chart view.
## ProjectSchedule
Create a Project Schedule in this worksheet. / Enter title of this project in cell B1. / Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. / Continue navigating down column A to hear further instructions.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3.	系统架构师之路	Project Start:		Wed, 7/6/2022
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. / The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. / You should not modify these cells. / Display Week: label is in cell C4.		Display Week:		1				Jul 4, 2022					Jul 11, 2022					Jul 18, 2022					Jul 25, 2022					Aug 1, 2022					Aug 8, 2022					Aug 15, 2022					Aug 22, 2022
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. / You should not modify these cells. / Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.					4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
This row contains headers for the project schedule that follows below them. / Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. / All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. / Do not modify content in cells within columns after column I starting with cell I7.	TASK	ASSIGNED / TO	PROGRESS	START	END		DAYS	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. / Enter a new Title in cell B8. / Enter a name to assign the phase to, if it applies for your project, in cell C8. / Enter Progress for the entire phase, if it applies for your project, in cell D8. / Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. / The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. / To delete the phase and work only from tasks, simply delete this row.	Phase 1 系统架构师通览
Cell B9 contains the sample task "Task 1." / Enter a new task name in cell B9. / Enter a person to assign the task to in cell C9. / Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. / Enter task start date in cell E9. / Enter task end date in cell F9. / A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9.	读教材		1%	7/6/22	10/4/22		91
Rows 10 through 13 repeat the pattern from row 9. / Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. / A sample of another phase starts in cell A14. / Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more.	看视频		66%	7/6/22	9/4/22		61
	做习题		0%	9/4/22	11/23/22		81
	练字体		10%	7/6/22	10/14/22		101
	看文章		2%	7/7/22	11/4/22		121
The cell at right contains the Phase 2 sample title. / You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. / To create a new phase block in this row, enter a new Title in cell at right. / To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. / Update the Phase details in cell at right based on cell A8's instruction. / Continue navigating down column A cells to learn more. / If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. / Repeat the instructions from cells A8 and A9 whenever you need to.	Phase 2 真题训练
	2022题目		0%	11/23/22	11/27/22		5
	2020题目		0%	11/25/22	11/30/22		6
	2019题目		0%	11/30/22	12/3/22		4
	2018题目		0%	11/30/22	12/2/22		3
	2017题目		0%	11/30/22	12/3/22		4
Sample phase title block	Phase 3 冲刺
	做案例			7/21/22	7/26/22		6
	刷视频			7/27/22	7/31/22		5
	翻笔记			8/1/22	8/6/22		6
	写论文			8/7/22	8/17/22		11
	看项目			8/1/22	8/5/22		5
Sample phase title block	Phase 4 赴考
	打印准考证			10/28/2022	10/28/2022		#VALUE!
	准备文具			10/28/2022	10/28/2022		#VALUE!
	测核酸			11/18/2022	11/18/2022		#VALUE!
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. / Insert new rows ABOVE this one to continue building out your Project Schedule.

## 基础
NO	科目	状态	计划时长（小时）	实际时长	参考书	参考视频	进度	备注
1	计算机原理		15.0	1.5	1、深入理解计算机系统（原书第3版） / 2、计算机组成原理 艾伦·克莱门茨 (Alan Clements) / 3、计算机是怎样跑起来的 / 4、程序是怎样跑起来的 / 5、计算机组成：结构化方法 Andrew S. Tanenbaum / 6、计算机体系结构：量化研究方法 / 7、程序员的自我修养：链接、装载和库 / 8、编码：隐匿在计算机软硬件背后的语言	1、北京大学Computer Organization / 2、	0.10
2	操作系统		20.0	0.5	1、Operating Systems Three Easy Pieces / 2、Thomas Anderson, Michael Dahlin - Operating Systems_ Principles and Practice / 3.Operating System Concepts 9th		0.03
3	数据库		15.0	0.5	1.数据库系统概念 / 2.SQLite Database System: Design and Implementation / 3.PostgreSQL 14 Administration Cookbook / 4.PostgreSQL Query Optimization		0.03
4	计算机网络		20.0	0.5	1.计算机安全:原理与实践(原书第三版） 威廉·斯托林斯 (William Stallings / 2.Al Anderson, Ryan Benedetti - Head First Networking / 3.Networking Essentials, 6th Edition (Beasley, Jeffrey, Nilkaew, Piyasat) / 4.图灵程序设计丛书图解TCPIP(第5版) (村山公保 竹下隆史 苅田幸雄 / 5.图解HTTP (上野宣) (z-lib.org)		0.03
5	系统性能		10.0	1.0			0.10
6	开发方法		20.0	0.5			0.03
7	系统规划		15.0	1.0			0.07
8	系统分析与设计		30.0	0.5			0.02
9	软件架构设计		35.0	0.5			0.01
10	设计模式	学习中	35.0	0.1	1.Head First Design Patterns_ Building Extensible and Maintainable Object-Oriented Software Eric Freeman, Elisabeth Robson / 2.图解设计模式		0.00
11	测试评审		10.0	0.2			0.02
12	嵌入式		5.0	0.0			0.00
13	开发管理		15.0	0.5			0.03
14	信息系统基础知识		20.0	1.0			0.05
15	中间件		10.0	0.5			0.05
16	安全及保密		5.0	0.5	1.计算机安全:原理与实践(原书第三版） 威廉·斯托林斯 (William Stallings		0.10
17	系统的可靠性分析与设计		20.0	0.5			0.03
18	软件的知识产权保护		10.0	0.1			0.01
19	标准化知识		5.0	0.1			0.02
20	应用数学		20.0	0.9			0.05
21	虚拟化、云计算与物联网		15.0	0.2			0.01
22	案例知识		50.0	0.5			0.01
23	论文		50.0	0.1			0.00
						总体进度	0.03

## 进阶
NO	科目	状态	计划时长	实际时长	参考书	参考视频	进度	备注
1	学牛人							https://martinfowler.com/architecture/
2	看原版				1.Software Architecture in Practice, 4th Edition / 2.Design It!_ From Programmer to Software Architecture
3	做开源							https://qlib.readthedocs.io/en/latest/introduction/introduction.html
4	弄项目							何处寻找？
								在具体工作中使用

## 应试
约束	备注
1、每周一主题	聚焦问题
2、每天一小时	时间投入
3、每月一刷题	用笔书写
4、每天一文章	书面表达